## Sheet1
Questions | Comments | Assigned To | Status
1. For a line item in CARR_INV_SHPMT_DTL table, if a tractor has total miles as zero , then we are defaulting it to one. Is this ok or do you suggest any other value.? | All the Zero miles line items need to ignored and the shuttle amount need to considered in Admin cost | Vineeth | closed
2. There is data in test environment, where there are two line items for same shipment id on same day, in CARR_INV_SHPMT_DTL table. Do we need roll up these line items or take it as individual shipments.? | In future , we will not have duplicates. As the shipment ID is 7 digit length now, if are facing this problem. | Teresa/Abbey | Closed
3. If there are two line items for same shipment ID , but on different days, then these are considered as two separate shipments with shpmt_id_1 and shpmt_id_2. Please confirm. | on hold for now | Teresa/ Abbey | Open
INV_CTGY_CD BREAKAGE-LOSS - exclude DFT-PALLET - DROPLOT- admin GLASS-SPOTTING OTHERCR - admin PKG-PALLET - PORT-ARLINGTON - exclude PORT-BELLINGHAM PORT-EUGENE PORT-HAYDEN PORT-MEDFORD PORT-MOSES LAKE PORT-PUYALLUP PORT-RENTON PORT-SALEM PORT-SPOKANE PORT-UNION GAP PORT-WENATCHEE RECYCLECR THRDPRTYTX - admin | Exclude all red hidhlighted codes | Teresa/ Abbey | closed
AB shipment ID are 7 digit long instead of 8 digit long | on hold for now | Teresa/ Abbey | Open
bud exchange Payment Visibility – FAP to SCD. 1) What are the tables for retrieving the data from the TM DB ? 2) What are the column value need to pull from the TM DB.? 3) What are the criteria for pulling the data from the TM DB? 4) What are the tables for inserting the data in to SCD DB.? | Waiting for clarifications | Teresa/Abbey | OPen